## Sheet1
Task ID | Task | Start | Finish | Responsible | %complete
1 | Decide on Project | January 10th | Febuary 20 | Sam and Jacob | 100
2 | Resarch API | Febuary 21 | Febuary 25 | Sam and Jacob | 100
3 | Create documentation and keep up with it | Febuary 21 | April 21st | Sam and Jacob | 100
4 | Create deliverables and divide tasks | Febuary 25 | March 1st | Sam and Jacob | 100
5 | Create Backend | March 1st | March 14th | Sam | 100
6 | QE Testing of backend | march 14th | March 21st | Sam | 100
7 | Deisgn Mock up of Front end | March 1st | March 21st | Jacob | 100
8 | create connection between server,frontend, and backend | March 21st | March 30th | Jacob | 100
9 | Test connection | Mach 30th | April 2nd | Jacob | 100
10 | Stylize | April 2nd | April 9th | Jacob | 100
11 | Final QE Testing of whole system | April 9th | April 20th | Sam and Jacob | 100
12 | Submit everything to GitHub | April 21st | April 21st | Sam and Jacob | 100